## Change Register
FDMS CHANGE REGISTER v1.2
Farm Decision Modelling Standard · living record of change-control candidates and rulings
Adopted edition in force: FDMS v1.2, adopted 5 August 2026. Nothing in this register amends v1.2. Rulings recorded 8 August 2026 by J. Mambozoukuni.
Change-control rule: a change may originate only from (1) reviewer or public comment, (2) implementation experience, (3) validation evidence, (4) new published evidence.
ID | Received | Source class | Originator | Provenance | Element(s) | Nature | Summary of the candidate | Ruling | Ruling date | Target edition | In force | Trigger effect | Calibration register effect | Status | Drafted where
CC-1 | 5 Aug 2026 | (2) Implementation experience | J. Mambozoukuni | Internal, author | E1 | Extension | No element explicitly requires declaration of currency, price basis, and real versus nominal terms. Candidate E1 boundary addition. | Open, not yet ruled |  | v1.3 candidate |  | None expected | None expected | OPEN | Not drafted
CC-2 | 5 Aug 2026 | (3) Validation evidence | Calibration exercise | Internal, author | E4 | Monitor | TE4.1 fires near universally across both calibration cases, making E4 Core in practice while Conditional on paper. | Monitor, no action | 8 Aug 2026 |  |  | None | None | MONITORING | n/a
CC-3 | 5 Aug 2026 | (3) Validation evidence | Calibration exercise | Internal, author | E14 | Monitor | Rewritten TE14.2 fires on virtually any input, rotation or tillage decision. The materiality branch is the pressure valve; watch whether it holds. | Monitor, no action | 8 Aug 2026 |  |  | None | None | MONITORING | n/a
CC-4 | 8 Aug 2026 | (4) New published evidence | Carolan (2026), Agricultural Systems 237:104830 | External, published | E1 or new element | Extension | Distinguishes model influence from objective influence and argues balanced performance requires periodically revising objective functions. Candidate re-specification trigger requiring the decision purpose to be re-examined on stated conditions. | Open, not yet ruled |  | v2.0 candidate |  | Would add a trigger | Would require re-run | OPEN | Not drafted
CC-5 | 8 Aug 2026 | (1) Reviewer or public comment | Anonymous 1 | EXTERNAL, unattributed | E9 | Defect correction | Shock library must be calibrated to the decision unit's own recent history before first use, or the shipped default retained and marked as an uncalibrated placeholder, each shock carrying its basis. E9 already asserts local values but its pass condition tests only the mechanism. | ACCEPTED IN PRINCIPLE | 8 Aug 2026 | v1.3 | 1 Feb 2027 | None. 29 triggers unchanged. | Counts stand. Both cases re-run before in force. | ACCEPTED, PENDING IMPLEMENTATION | CC5/6/7 proposals doc, s.2D
CC-6 | 8 Aug 2026 | (1) Reviewer or public comment | Internal expert reviewer (agronomist) | INTERNAL to the practice | E12 | Extension, authored not evidenced | Retained output stated in physical terms with avoided-purchase value reported separately, labelled non-cash, excluded from cash results and every headline figure. Disclosure and exclusion rule, not a valuation rule. | ACCEPTED IN PRINCIPLE | 8 Aug 2026 | v1.3 | 1 Feb 2027 | None. TE7.4 already activates. | Counts stand. Case A re-run; Case B unaffected. | ACCEPTED, PENDING IMPLEMENTATION | CC5/6/7 proposals doc, s.3D
CC-6a | 8 Aug 2026 | (1) Reviewer or public comment | Sub-ruling on CC-6 | n/a | E12 | Drafting decision | Whether the CC-6 obligation fires on any retention or is bounded by materiality. | BOUNDED BY THE J1 PROPORTIONALITY CONVENTION, no numeric threshold | 8 Aug 2026 | v1.3 | 1 Feb 2027 | None | None | RULED | CC5/6/7 proposals doc, s.3E
CC-7 | 8 Aug 2026 | (1) Reviewer or public comment | Internal expert reviewer (agronomist) | INTERNAL to the practice | E5, cross-ref E12 | Extension | Where any registered scenario values own labour, land or water at zero, the model states that the result is a return to owned resources and not economic profit, and reports the break-even valuation at which the advantage disappears. | ACCEPTED IN PRINCIPLE | 8 Aug 2026 | v1.3 | 1 Feb 2027 | None | Counts stand. Both cases re-run; Case A not assumed to pass. | ACCEPTED, PENDING IMPLEMENTATION | CC5/6/7 proposals doc, s.4D
CC-7a | 8 Aug 2026 | (1) Reviewer or public comment | Sub-ruling on CC-7 | n/a | E5 / E12 | Drafting decision | Whether the CC-7 obligation sits in E5 (Core, reaches commercial models valuing owner-manager time at zero) or E12 (household layer, conditional on TE7.4). | E5, WITH A CROSS-REFERENCE FROM E12 | 8 Aug 2026 | v1.3 | 1 Feb 2027 | None | None | RULED | CC5/6/7 proposals doc, s.4E
E-1 | 11 Aug 2026 | (1) Reviewer or public comment | External reader comment, relayed during AARES abstract review | External, unattributed | Standard s.3 (evidence grounding statement) | Erratum (defect correction) | Section 3 states fifteen sources across seven streams, then enumerates what reads as eight categories: climate-smart appraisal is listed separately from agricultural investment appraisal, and the register label multi-criteria farm design is omitted. Component Map ground truth (Evidence_Register.xlsx): seven coding columns; climate-smart codes within investment appraisal, multi-criteria within farm-systems. The count is correct; the enumeration is defective. | ACCEPTED AS ERRATUM. Corrected enumeration published as Erratum Notice No. 1; the Standard text correction lands in v1.3 (the adopted edition is frozen). Foundations working draft corrected directly (unpublished). WP 2026-01 v1.2 restates the count only and is unaffected. | 12 Aug 2026 | v1.3 | 1 Feb 2027 | None | None. 16/3/29/2 stands; no trigger or coding touched. | ERRATUM PUBLISHED, TEXT CORRECTION PENDING v1.3 | Erratum Notice No. 1

## Governance
AMENDMENT WINDOW AND TRANSITION
Decision | Ruling | Ruled | Basis
T1 Amendment timing | Fixed annual window, not ad hoc patching. Comments close 30 November 2026; ruling and drafting through December 2026; FDMS v1.3 in force 1 February 2027. | 8 Aug 2026 | The credibility of a standard adopted five days ago rests on the freeze holding. Amending within a week on a sample of two reviewers, one internal, would teach users that the adopted edition is provisional.
T2 Transition for v1.2 claims | Conformance claims may be made against FDMS v1.2 until 1 February 2028. A claim made against an edition remains correctly made for the life of the model. | 8 Aug 2026 | Twelve months is the conventional transition window and there is no reason to be shorter.
T3 Publish disposition ahead of amendment | Yes. Comment Disposition Record No. 1 issued 8 August 2026, covering all material from both reviews and not only the standard-level items. | 8 Aug 2026 | A disposition record demonstrates the governance machinery working, which is what a new standard most needs to show and what almost no new standard can show.
Pre-condition on all three accepted items | Reference Workbook v1.2.2 must demonstrate each proposed obligation before it becomes binding, and both calibration cases must be re-run against amended text before the in-force date, with the result published whatever it is. | 8 Aug 2026 | A requirement that survives demonstration in a working model at reasonable cost is a requirement. One that does not is a good intention.

## Provenance
REVIEW BASE, RECORDED FOR THE VALIDATION FILE
This sheet exists so that no future validation claim can describe the review base more favourably than it is.
Reviewer | Class | Relationship to the practice | Length | Scope | May be counted as independent external review
Anonymous 1 | External, unattributed | None known | approx. 900 words | Standard and reference workbook | Yes, with the qualification that the reviewer is unattributed
Internal expert reviewer (agronomist) | Internal expert review | Auctus agronomy specialist | approx. 3,300 words | Reference workbook, audited formula by formula, with standard-level implications | NO. Internal expert review is evidence of a different class and must never be counted as independent external review in Foundations s.9 or any validation claim.
v1.2 of this register (12 Aug 2026): adds row E-1, the first erratum, arising from an external reader comment during AARES 2027 abstract preparation. No ruling of v1.1 is altered; the file version changes because the register is change-controlled with the standard.